## Construction Estimate Example
Project Name: | Pre-Engineered Steel Building | Architect: | As Shown
Location: | Anywhere, USA | [5 empty] | 01/01/12
Line Number | Description | Qty | Unit | Material | Labor | Equipment | SubContract | EstimateTotal
03 30 53.40 3950 | Strip footing, 12" x 36" | 33.33 | C.Y. | 4699.53 | 2383.1 | 14.33 | 0
03 30 53.40 3940 | Strip footing, 12" x24" | 14.8 | C.Y. | 2175.6 | 1324.6 | 7.99 | 0
03 31 05.35 0300 | Concrete ready mix, 4000 psi, for slab | 185.2 | C.Y. | 19631.2 | 0 | 0 | 0
03 31 05.70 4300 | Placing concrete, slab on grade | 185.2 | C.Y. | 0 | 2666.88 | 87.04 | 0
03 11 13.65 3000 | Concrete forms | 500 | L.F. | 190 | 1010 | 0 | 0
03 22 05.50 0200 | WWF | 150 | C.S.F. | 3975 | 3450 | 0 | 0
03 39 23.13 0300 | Curing | 150 | C.S.F. | 787.5 | 795 | 0 | 0
03 35 29.30 0250 | Concrete finishing | 15000 | S.F. | 0 | 7500 | 300 | 0
03 35 29.35 0160 | Control joints | 650 | L.F. | 84.5 | 247 | 58.5 | 0
Division 03 | Subtotal |  |  | 31543.33 | 19376.58 | 467.86 | 0 | 51387.77
08 33 23.10 0100 | 10' x 10' OH Door | 8 | Ea. | 14000 | 4080 | 0 | 0
08 33 23.10 3300 | Add for enamel finish | 800 | S.F. | 1216 | 0 | 0 | 0
Division 8 | Subtotal |  |  | 15216 | 4080 | 0 | 0 | 19296
13 34 19.50 1000 | Pre-Engineered Steel Building | 15000 | SF Flr. |  |  |  | 287250
13 34 19.50 6050 | Framing for doors, 3' x 7' | 4 | Opng. | 0 | 0 | 0 | 1900
13 34 19.50 6100 | Framing for doors, 10' x 10' | 8 | Opng. | 0 | 0 | 0 | 8400
13 34 19.50 6200 | Framing for windows, 3' x 4' | 6 | Opng. | 0 | 0 | 0 | 3450
13 34 19.50 5750 | PESB doors | 4 | Opng. | 1740 | 572 | 0 | 0
13 34 19.50 7750 | PESB windows | 6 | Opng. | 2100 | 483 | 61.8 | 0
13 34 19.50 6550 | Gutters | 380 | L.F. | 2679 | 851.2 | 0 | 0
13 34 19.50 8650 | Roof vent | 15 | Ea. | 382.5 | 2685 | 0 | 0
13 34 19.50 6900 | Insulation | 25000 | S.F. | 12750 | 7000 | 0 | 0
Division 13 | Subtotal |  |  | 19651.5 | 11591.2 | 61.8 | 301000 | 332304.5
Estimate Subtotal |  |  |  | 66410.83 | 35047.78 | 529.66 | 301000 | 402988.27
|  | Gen. Reqirements |  | 4648.7581 | 2453.3446 | 37.0762 | 21070
|  | Sales Tax |  | 3320.54 |  | 26.48 | 7525
|  | Subtotal |  | 74380.1281 | 37501.1246 | 593.2162 | 329595
|  | GC O & P |  | 7438.0128 | 3750.1125 | 59.3216 | 32959.5
|  | Subtotal |  | 81818.1409 | 41251.2371 | 652.5378 | 362554.5 | 486276.4158
|  | Contingency |  | @ | 5% |  |  | 24313.8208
|  | Subtotal | [5 empty] | 510590.2366
|  | Bond |  | $12/1000 +10% O&P |  |  |  | 6739.7911
|  | Subtotal | [5 empty] | 517330.0277
|  | Location Adjustment |  |  | Factor | 102.3 |  | 11898.5906
|  | Grand Total | [5 empty] | 529228.6183

## Text
CONSTRUCTION ESTIMATE
There are as many estimate formats as there are estimators. This sample is provided to demonstrate the major elements of an estimate, including a tally of the Means data lines, and a summary of the typical mark-ups on a contractor’s work to arrive at a total cost to the owner. The Means Location Factor is added at the bottom of the estimate to adjust the cost of the work to a specific location. This example shows the cost to construct a pre-engineered steel building. The foundation, doors, windows and insulation will be installed by the GC. A subcontractor will install the sructural steel, roofing and siding.
This estimate is based on an interactive Excel spreadsheet. A copy of this spreadsheet is located on Means web-site at www.rsmeans.com/xxxxxx. You are free to download it and adjust it to your methodology.
Work Performed: The body of the estimate shows the Means data selected, including line number, a brief description of each item, it’s take-off unit and quantity, and the bare costs of materials, labor and equipment. This estimate also includes a column titled ‘SubContract’. This data is taken from the Means column ‘Total Incl O&P’, and represents the total that a sub-contractor would charge a general contractor for his work, including the sub’s markup for overhead and profit.
Sales Tax: If the work is subject to state or local sales taxes, the amount must be added to the estimate. Sales tax may be added to material costs, equipment costs, and sub-contracted work. In this case, sales tax was added in all three categories. It was assumed that approximately half the sub-contracted work would be material cost, so the tax was applied to 50% of the subcontract total.
GC O&P: This entry represents the General Contractor's mark-up on material, labor, equipment and subcontractor costs. Means standard mark-up on materials, equipment and subcontracted work is 10%. The Means mark-up on the labor performed by the GC's workers is the 'Skilled Workers Average' shown in Column F on the table 'Installing Contractor's Overhead & Profit', which can be found on the inside-back cover of the book.
Contingency: A factor for contingency may be added to any estimate to represent the cost of unknowns that may occur between the time that the estimate is performed and the time the project is constructed. The amount of the allowance will depend on the stage at which the estimate is done, and the contractor's assessment of the risk involved. At the conceptual stage a contingency allowance of 20% is typical; 15% during schematic design, and 10% during the contract document stage are typical. After bid and during construction an allowance of 3% is typical.
Bonds: Bond costs should be added to the estimate. The figures here represent a typical performance bond, insuring the owner that if the General Contractor does not complete his obligations in the construction contract the bonding company will pay the cost for completion of the work.
Location Adjustment: Means published data is based on national average costs. If necessary, adjust the total cost of the project using a location factor from the 'Location Factor' table or the 'City Cost Index' table. Use Location Factors if the work is general, covering multiple trades. If the work is by a single trade (eg. masonry) use the more specific data found in the City Cost Indexes.
General Requirements: This item covers project-wide needs provided by the general contractor. These items vary by project, but may include temporary facilities and utilities, security, testing, project clean-up, etc. For small projects a percentage is generally used, typically between 5% and 15% of project cost. For large projects the costs may be itemized and priced individually.

## Generic Example
Project Name: | Pre-Engineered Steel Building | Architect: | As Shown
Location: | Anywhere, USA | [5 empty] | 01/01/12
Line Number | Description | Qty | Unit | Material | Labor | Equipment | SubContract | EstimateTotal
03 30 53.40 3950 | Strip footing, 12" x 36" | 33.33 | C.Y. | 4699.53 | 2383.1 | 14.33 | 0
03 30 53.40 3940 | Strip footing, 12" x24" | 14.8 | C.Y. | 2175.6 | 1324.6 | 7.99 | 0
03 31 05.35 0300 | Concrete ready mix, 4000 psi, for slab | 185.2 | C.Y. | 19631.2 | 0 | 0 | 0
03 31 05.70 4300 | Placing concrete, slab on grade | 185.2 | C.Y. | 0 | 2666.88 | 87.04 | 0
03 11 13.65 3000 | Concrete forms | 500 | L.F. | 190 | 1010 | 0 | 0
03 22 05.50 0200 | WWF | 150 | C.S.F. | 3975 | 3450 | 0 | 0
03 39 23.13 0300 | Curing | 150 | C.S.F. | 787.5 | 795 | 0 | 0
03 35 29.30 0250 | Concrete finishing | 15000 | S.F. | 0 | 7500 | 300 | 0
03 35 29.35 0160 | Control joints | 650 | L.F. | 84.5 | 247 | 58.5 | 0
Division 03 | Subtotal |  |  | 31543.33 | 19376.58 | 467.86 | 0 | 51387.77
08 33 23.10 0100 | 10' x 10' OH Door | 8 | Ea. | 14000 | 4080 | 0 | 0
08 33 23.10 3300 | Add for enamel finish | 800 | S.F. | 1216 | 0 | 0 | 0
Division 08 | Subtotal |  |  | 15216 | 4080 | 0 | 0 | 19296
13 34 19.50 1000 | Pre-Engineered Steel Building | 15000 | SF Flr. | 0 | 0 | 0 | 287250
13 34 19.50 6050 | Framing for doors, 3' x 7' | 4 | Opng. | 0 | 0 | 0 | 1900
13 34 19.50 6100 | Framing for doors, 10' x 10' | 8 | Opng. | 0 | 0 | 0 | 8400
13 34 19.50 6200 | Framing for windows, 3' x 4' | 6 | Opng. | 0 | 0 | 0 | 3450
13 34 19.50 5750 | PESB doors | 4 | Opng. | 1740 | 572 | 0 | 0
13 34 19.50 7750 | PESB windows | 6 | Opng. | 2100 | 483 | 61.8 | 0
13 34 19.50 6550 | Gutters | 380 | L.F. | 2679 | 851.2 | 0 | 0
13 34 19.50 8650 | Roof vent | 15 | Ea. | 382.5 | 2685 | 0 | 0
13 34 19.50 6900 | Insulation | 25000 | S.F. | 12750 | 7000 | 0 | 0
Division 13 | Subtotal |  |  | 19651.5 | 11591.2 | 61.8 | 301000 | 332304.5
Estimate Subtotal |  |  |  | 66410.83 | 35047.78 | 529.66 | 301000 | 402988.27
|  | Gen. Reqirements |  | 4648.7581 | 2453.3446 | 37.0762 | 21070
|  | Sales Tax |  | 3320.54 |  | 26.48 | 7525
|  | Subtotal |  | 74380.1281 | 37501.1246 | 593.2162 | 329595
|  | GC O & P |  | 7438.0128 | 3750.1125 | 59.3216 | 32959.5
|  | Subtotal |  | 81818.1409 | 41251.2371 | 652.5378 | 362554.5 | 486276.4158
|  | Contingency |  | @ | 5% |  |  | 24313.8208
|  | Subtotal | [5 empty] | 510590.2366
|  | Bond |  | $12/1000 +10% O&P |  |  |  | 6739.7911
|  | Subtotal | [5 empty] | 517330.0277
|  | Location Adjustment |  |  | Factor | 102.3 |  | 11898.5906
|  | Grand Total | [5 empty] | 529228.6183